## Sheet1
SUBTEAM | TASKS | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | DUE
|  | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03
Frontend | Interview | 2023-03-13: Consultation; 2023-03-14: Send out interview requests/questions; 2023-03-18: Consolidate all interview responses for backend
| Build HTML | 2023-03-13: Build test app with small data subset; 2023-03-17: Implement more flight data viz options before meeting; 2023-03-22: Get model and data from backend; 2023-03-24: Implement skeleton interactive viz based on model and actual data
| Dockerize | 2023-03-24: Integrate frontend, backend during meeting
Backend |  | 2023-03-13: Consultation; 2023-03-14: Send supplementary interview questions to frontend
| Modelling | 2023-03-17: Finish creating models draft 1 before meeting
| Database | 2023-03-17: Setup database on aws
Viz plots
| Dockerize | 2023-03-24: Integrate frontend, backend during meeting